## Issue Log
Project Issue Tracking Log | [10 empty] | Last Update: |  | 2006-08-25
Project ID: | SAA8062001 |  | Project Name: |  | ATP |  | Project Dept.: |  | SED |  | Project Manager: |  | David Yu
No | Source | Involved Parties | Category | Issuer | Description | Action | Owner | Issue Date | Due Date | Finished Date | Priority | Status | Verifier | Escalation Path | Note
IL001 | Maintenance Record | ChiDu Factory | MMI | TRA | 1.Touch Screen電路經常被括傷 2.TRA反應MMI有反光現象, 且貼上保護貼後更嚴重 | 尋求能耐候至-5。C ~ 65。C及無反光之保護貼 1.領航家提供Sample, 8/11已通過TRA Mr. Huang初步確認, 8/18至彰化機務務段在車上與TRA承辦人及司機員作雙向確認後，承辦人再要求提供10片並安裝列車上[嘉義、彰化、新竹機務段各一組]作驗證測試。 | 李德明/俞光回 | 2006-07-31 | 2006-09-04 |  | Medium | Open |  | PM
IL002 | Maintenance Record | ChiDu Factory | MMI | 俞光回 | Touch Screen 經常須校正 | Touch Screen兩層之接合面接觸不良問題, 向3M尋求解決之道. 1.將改用墊片取代矽利康, 以免Touch Screen被硬性固定在面板上, 李處長分析可行性及可靠度無問題, 維修時將同步改善, 並列入追蹤。 2.提供六台修正後MMI並貼上防眩光保護貼分別安裝列車上[嘉義、彰化、新竹機務段各一組]作驗證測試。 | 李德明 | 2006-07-31 | 2006-09-04 |  | Critical | Open | 俞光回 | PM
IL003 | Maintenance Record | ChiDu Factory | MS | 俞光回 | 司機員隨身碟(MS)及USB公座, 損壞率過高 (防呆裝置及公母頭口徑差距過大, 造成User有扭轉空間而導致彈簧夾片鬆弛及母頭破裂) | 1.在MS上加印紅色螢光箭頭標誌, 以利司機員辨識. a.備品不足, 擬重新加作MS約500 Sets. b.MS母頭材質須加強. (USB OTI Chip代理商已連繫上, 待MS機構改良後, 即可進行製造) 2.改善USB公座, 另製作一轉接頭約1000 Sets. a.No.11六角螺絲須改為3.5mm厚. b.No.12銘板改用紅色螢光箭頭. c.轉接頭母頭材質須加強. d.防呆裝置及公母頭口徑差距要減小 (TRA要求提供Prototype, 已於8/16向錩鋼order 1 set) | 李德明/何仁田 | 2006-07-31 | 2006-09-04 |  | Critical | Open |  | PM
Note on A3: 流水號
Note on B3: 填寫會議記錄編號、需求單號、或其他來源文件編號等。
Note on C3: 相關組織或公司
Note on D3: 子系統或問題類別
Note on E3: 提出者
Note on F3: 問題描述
Note on G3: 矯正措施
Note on H3: 負責人
Note on I3: 提出日期
Note on I4: Double click to select date
Note on I5: Double click to select date
Note on I6: Double click to select date
Note on I7: Double click to select date
Note on I8: Double click to select date
Note on I9: Double click to select date
Note on I10: Double click to select date
Note on I11: Double click to select date
Note on I12: Double click to select date
Note on I13: Double click to select date
Note on I14: Double click to select date
Note on I15: Double click to select date
Note on I16: Double click to select date
Note on I17: Double click to select date
Note on I18: Double click to select date
Note on I19: Double click to select date
Note on I20: Double click to select date
Note on J3: 到期日
Note on J4: Double click to select date
Note on J5: Double click to select date
Note on J6: Double click to select date
Note on J7: Double click to select date
Note on J8: Double click to select date
Note on J9: Double click to select date
Note on J10: Double click to select date
Note on J11: Double click to select date
Note on J12: Double click to select date
Note on J13: Double click to select date
Note on J14: Double click to select date
Note on J15: Double click to select date
Note on J16: Double click to select date
Note on J17: Double click to select date
Note on J18: Double click to select date
Note on J19: Double click to select date
Note on J20: Double click to select date
Note on K3: 完成日期
Note on K4: Double click to select date
Note on K5: Double click to select date
Note on K6: Double click to select date
Note on K7: Double click to select date
Note on K8: Double click to select date
Note on K9: Double click to select date
Note on K10: Double click to select date
Note on K11: Double click to select date
Note on K12: Double click to select date
Note on K13: Double click to select date
Note on K14: Double click to select date
Note on K15: Double click to select date
Note on K16: Double click to select date
Note on K17: Double click to select date
Note on K18: Double click to select date
Note on K19: Double click to select date
Note on K20: Double click to select date
Note on M3: 狀態
Note on N3: 驗證或確認人員
Note on O3: David Yu: 問題升級之等級