## Training Plan
Project Name Skill and Training Plan
Last Update: 06/02/2005
Role |  |  |  | Customer POC | Quality Assurance Manager | Project Manager |  | Task Leader |  |  | Requirement Engineer |  | Schedule/Cost/Resource Manager |  | Risk Manager |  | Communication Manager |  | System Engineer - Architect |  | System Engineer - Interface | System Engineer - CSD/SEM | Design Engineer |  |  | Developer/Programmer |  | Integration Engineer |  | CM Manager | Doc. Manager | System Assurance(RAMS) | Measurement Data Collector | Installation |  |  | Testing Manager |  | Subcontract Manager
System/Subsystem - Employee Skill/Training Plan |  |  |  | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name | Name
Technical Skill | System Engineering - OS | Linux, Windows | Plan Date | [22 empty] | 12/2004
Actual Date
| System Engineering - DBA | SQL | Plan Date | [23 empty] | 01/2005
Actual Date
| System Engineering - Network | LAN design and management knowledge | Plan Date | [19 empty] | 06/2005
Actual Date
| System Analysis/Design | Analysis and design skill | Plan Date | [19 empty] | 06/2005 | 03/2005 | 03/2005
Actual Date
| Development - Coding | C, PLC, OPC, … | Plan Date |  |  |  |  | 05/2005 | [16 empty] | 04/2005 | 04/2005 | 04/2005
|  |  | Actual Date |  |  |  |  | 05/12/2005
| Testing | Test technology | Plan Date | [19 empty] | 06/2005 | 05/2005 | 05/2005 | 05/2005 | 05/2005 | 05/2005 | 05/2005 |  |  |  |  | 05/2005 | 06/2005 | 06/2005 | 05/2005 | 05/2005
Actual Date
| Wireless LAN | WLAN technology | Plan Date | [5 empty] | 06/2005 | [16 empty] | 06/2005
Actual Date
| Communication | Tele communication concept | Plan Date |  |  |  |  | 06/2005 | 06/2005 | 09/2004 |  | 09/2004 | [9 empty] | 09/2004 | 06/2005 | 09/2004 | 09/2004 | 09/2004 | 09/2004 | 09/2004 | 09/2004 | 06/2005 | 09/2004 | 09/2004 |  | 09/2004 | 06/2005 | 06/2005 | 09/2004 | 09/2004 | 09/2004 | 09/2004
|  |  | Actual Date |  |  |  |  | 05/17/2005 | 05/17/2005 | 05/17/2005 |  | 05/17/2005 | [9 empty] | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 |  | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005 | 05/17/2005
| PSD Knowledge | Power supply system concept | Plan Date |  |  |  |  | 06/2005 |  | 08/2004 | 08/2004 | [10 empty] | 08/2004 |  | 08/2004 | 08/2004 |  | 08/2004 | 08/2004 | 08/2004 | 06/2005 | 08/2004 | 08/2004 |  | 08/2004 | 06/2005 | 06/2005 | 08/2004 | 08/2004 | 08/2004 | 08/2004
|  |  | Actual Date |  |  |  |  | 05/24/2005 |  | 05/24/2005 | 05/24/2005 | [10 empty] | 05/24/2005 |  | 05/24/2005 | 05/24/2005 |  | 05/24/2005 | 05/24/2005 | 05/24/2005 | 05/24/2005 | 05/24/2005 | 05/24/2005 |  | 05/24/2005 | 05/24/2005 | 05/24/2005 | 05/24/2005 | 05/24/2005 | 05/24/2005 | 05/24/2005
| RAMS | System assurance knowledge | Plan Date | [6 empty] | 07/2004 | [21 empty] | 07/2004
|  |  | Actual Date | [6 empty] | 08/22/2004